## GFA cycle 03 2021
Gulu GFA Cycle 03, 2021 Distribution Update
Date: | 2021-03-16
Data | Population
Day's Distribution Summary
| Distribution Date | Total |  |  | Modality Ratio |  |  | Overall Status | [6 empty] | 2021-03-16
| Modality | Cash | Food |  | Cash | Food |  | Cash |  |  | Food |  |  |  | Cash | % Cash | Food | % Food
Settlement | FDP | [6 empty] | Population | % Cash | Status | Population | % Food | Status
Adjumani East | Ayilo 2 | 10907 | 4786 |  | 69.5% | 30.5% |  | 10724 | 98.32% | Complete | 4677 | 97.72% | Complete
| Ayilo 1 | 22088 | 6176 |  | 78.15% | 21.85% |  | 16250 | 73.57% | Ongoing | 5558 | 89.99% | ongoing |  | 5596 | 25.34% | 1924 | 31.15%
| Alere | 6758 | 1521 |  | 81.63% | 18.37% |  | 6500 | 96.18% | Ongoing | 1409 | 92.64% | ongoing |  | 6500 | 96.18% | 1409 | 92.64%
| Baratuku | 6239 | 1756 |  | 78.04% | 21.96% |  | 5739 | 91.99% | Ongoing | 1279 | 72.84% | ongoing |  | 5739 | 91.99% | 1279 | 72.84%
| Boroli | 11515 | 3049 |  | 79.06% | 20.94% |  | 11286 | 98.01% | Complete | 2960 | 97.08% | Complete
| Nyumanzi | 33464 | 7228 |  | 82.24% | 17.76% |  | 30558 | 91.32% | ongoing | 6800 | 94.08% | ongoing |  | 11574 | 34.59% | 2238 | 30.96%
| Olua | 7205 | 2072 |  | 77.67% | 22.33% |  | 7131 | 98.97% | Complete | 2021 | 97.54% | Complete
| Pagirinya 2 | 15710 | 20218 |  | 43.73% | 56.27% |  | 15507 | 98.71% | Complete | 19752 | 97.7% | Complete |  | 245 | 1.56% | 2077 | 10.27%
Adjumani West | Agojo | 3066 | 4140 |  | 42.55% | 57.45% |  | 3004 | 97.98% | Complete | 4005 | 96.74% | Complete
| Mungula 1 | 5785 | 746 |  | 88.58% | 11.42% |  | 5735 | 99.14% | Complete | 722 | 96.78% | Complete
| Mirieyi | 5175 | 1980 |  | 72.33% | 27.67% |  | 5139 | 99.3% | Complete | 1917 | 96.82% | Complete
| Maaji 1 | 483 | 66 |  | 87.98% | 12.02% |  | 476 | 98.55% | Complete | 66 | 100% | Complete
| Maaji 2 | 12314 | 4394 |  | 73.7% | 26.3% |  | 12118 | 98.41% | Complete | 4247 | 96.65% | Complete
| Maaji 3 | 11646 | 3484 |  | 76.97% | 23.03% |  | 11377 | 97.69% | Complete | 3331 | 95.61% | Complete |  | 4490 | 38.55% | 1552 | 44.55%
TOTAL |  | 152355 | 61616 |  | 71.2% | 28.8% |  | 141544 | 92.9% | Complete | 58744 | 95.34% | Complete |  | 34144 | 22.41% | 10479 | 17.01%
Daily Distribution Summaries
| Distribution Date | 2021-03-09 |  |  |  | 2021-03-10 |  |  |  | 2021-03-11 |  |  |  | 2021-03-12 |  |  |  | 2021-03-15 |  |  |  | 2021-03-16
| Modality | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | %Cash | Food | %Food | Cash | Cash% | Food | Food% | Cash | Cash% | Food | Food%
Settlement | FDP
Adjumani East | Ayilo 2 | 6213 | 56.96% | 2291 | 47.87% | 4511 | 41.36% | 1942 | 40.58% |  |  | 444 | 9.28%
| Ayilo 1 | [12 empty] | 4053 | 18.9% | 1475 | 25.25% | 6601 | 29.61% | 2159 | 36.16% | 5596 | 25.34% | 1924 | 31.15%
| Alere | [20 empty] | 6500 | 96.18% | 1409 | 92.64%
| Baratuku | [20 empty] | 5739 | 91.99% | 1279 | 72.84%
| Boroli |  |  |  |  | 4213 | 36.19% | 1533 | 53.49% | 6624 | 56.9% | 1194 | 41.66% | 451 | 3.92% | 233 | 7.6%
| Nyumanzi | [8 empty] | 4955 | 14.61% | 1675 | 24.48% | 3265 | 9.67% | 123 | 10.55% | 10737 | 31.89% | 2060 | 29.46% | 11574 | 34.59% | 2238 | 30.96%
| Olua | [12 empty] | 4110 | 55.42% | 1085 | 58.49% | 3021 | 41.93% | 924 | 44.59%
| Pagirinya 2 |  |  |  |  | 3690 | 23.22% | 4157 | 20.78% | 5006 | 31.5% | 4937 | 24.78% | 2575 | 16.25% | 2665 | 13.28% | 3991 | 25.38% | 5896 | 29.2% | 245 | 1.56% | 2077 | 10.27%
Adjumani West | Agojo |  |  |  |  | 2667 | 86.99% | 2541 | 61.38% | 340 | 11.09% | 1464 | 35.36%
| Mungula 1 |  |  |  |  | 5735 | 99.14% | 722 | 96.78%
| Mirieyi | [16 empty] | 5139 | 99.3% | 1917 | 96.82%
| Maaji 1 | 476 | 98.55% | 66 | 100%
| Maaji 2 |  |  |  |  | 5216 | 41.9% | 1942 | 45.61% | 5934 | 47.66% | 1841 | 43.24% | 968 | 7.86% | 464 | 10.56%
| Maaji 3 | [16 empty] | 6,880 7 | 58.01% | 1779 | 56.01% | 4490 | 38.55% | 1552 | 44.55%
TOTAL |  | 6689 | 4.39% | 2357 | 3.825% | 26032 | 17.09% | 12837 | 20.83% | 22859 | 15% | 11555 | 18.75% | 15422 | 10.12% | 6045 | 9.811% | 29489 | 19.36% | 14735 | 23.91% | 34144 | 22.41% | 10479 | 17.01%

## GFA Cycle 02 2021
Gulu GFA Cycle 02, 2021 Distribution Update
Date: | 2021-02-18
Data | Population
| Distribution Date | Total |  |  | Modality Ratio |  |  | Overall Status | [6 empty] | 2021-02-18
| Modality | Cash | Food |  | Cash | Food |  | Cash |  |  | Food |  |  |  | Cash | % Cash | Food | % Food
Settlement | FDP | [6 empty] | Population | % Cash | Status | Population | % Food | Status
Kiryandongo | Magamaga | 26187 | 6831 |  | 79.31% | 20.69% |  | 26040 | 99.44% | Complete | 6718 | 98.35% | Complete |  | 2955 | 11.28% | 462 | 6.763%
| Youth Centre | 26683 | 10481 |  | 71.8% | 28.2% |  | 26448 | 99.12% | Complete | 10284 | 98.12% | Complete
Palabek | Zone 1 |  | 5337 |  | 0% | 100% |  |  |  |  | 5196 | 97.36% | Complete
| Zone 5 |  | 17512 |  | 0% | 100% |  |  |  |  | 17085 | 97.56% | Complete
| Zone 4 |  | 25651 |  | 0% | 100% |  |  |  |  | 24726 | 96.39% | Complete
TOTAL |  | 52870 | 65812 |  | 44.55% | 55.45% |  | 52488 | 99.28% |  | 64009 | 97.26% |  |  | 2955 | 5.589% | 462 | 0.702%
Daily Distribution Summaries
| Distribution Date | 2021-02-08 |  |  |  | 2021-02-09 |  |  |  | 2021-02-10 |  |  |  | 2021-02-11 |  |  |  | 2021-02-12 |  |  |  | 2021-02-15 |  |  |  | 2021-02-16 |  |  |  | 2021-02-17 |  |  |  | 2021-02-18
| Modality | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food
Settlement | FDP
Kiryandongo | Magamaga | [20 empty] | 7393 | 28.23% | 2190 | 32.06% | 6987 | 26.68% | 1429 | 20.92% | 8705 | 33.24% | 2637 | 38.6% | 2955 | 11.28% | 462 | 6.763%
| Youth Centre | 6440 | 24.14% | 2970 | 28.34% | 9330 | 34.97% | 3556 | 33.93% | 7236 | 27.12% | 2734 | 26.09% | 3442 | 12.9% | 1024 | 9.77%
Palabek | Zone 1 |  |  | 2753 | 51.58% |  |  | 2443 | 45.77%
| Zone 5 | [10 empty] | 5329 | 30.43% |  |  | 3644 | 20.81% |  |  | 3166 | 18.08% |  |  | 3069 | 17.53% |  |  | 1877 | 10.72%
| Zone 4 |  |  | 3617 | 14.1% |  |  | 4337 | 16.91% |  |  | 4636 | 18.07% |  |  | 4473 | 17.44% |  |  | 2926 | 11.41% |  |  | 3567 | 13.91% |  |  | 1170 | 4.561%
TOTAL |  | 6440 | 12.18% | 9340 | 14.19% | 9330 | 17.65% | 10336 | 15.71% | 7236 | 13.69% | 12699 | 19.3% | 7168 | 13.7% | 5733 | 8.825% | 0 | 0% | 6092 | 9.257% | 7393 | 13.98% | 8826 | 13.41% | 6987 | 13.22% | 4476 | 6.801% | 8705 | 16.46% | 2637 | 4.007% | 2955 | 5.589% | 462 | 6.249%

## GFA Cycle 01 2021
Gulu GFA Cycle 01, 2021 Distribution Update
Date: | 2021-01-11
Data | Population
Day's Distribution Summary
| Distribution Date | Total |  |  | Modality Ratio |  |  | Overall Status | [6 empty] | 2021-01-11
| Modality | Cash | Food |  | Cash | Food |  | Cash |  |  | Food |  |  |  | Cash | % Cash | Food | % Food
Settlement | FDP | [6 empty] | Population | % Cash | Status | Population | % Food | Status
Adjumani East | Ayilo 2 | 10172 | 4305 |  | 70.26% | 29.74% |  | 10092 | 99.21% | Complete | 4227 | 98.19% | Complete
| Ayilo 1 | 20912 | 6104 |  | 77.41% | 22.59% |  | 20635 | 98.68% | Complete | 5990 | 98.13% | Complete |  | 3548 | 16.97% | 1377 | 22.56%
| Alere | 6587 | 1652 |  | 79.95% | 20.05% |  | 6563 | 99.64% | Complete | 1630 | 98.67% | Complete |  | 1978 | 30.03% | 452 | 27.36%
| Baratuku | 6247 | 1750 |  | 78.12% | 21.88% |  | 6134 | 98.19% | Complete | 1712 | 97.83% | Complete
| Boroli | 11317 | 3204 |  | 77.94% | 22.06% |  | 10946 | 96.72% | Complete | 3045 | 95.04% | Complete
| Nyumanzi | 33437 | 7197 |  | 82.29% | 17.71% |  | 33302 | 99.6% | Complete | 7115 | 98.86% | Complete |  | 4046 | 12.1% | 493 | 6.85%
| Olua | 7170 | 2117 |  | 77.2% | 22.8% |  | 7043 | 98.23% | Complete | 2056 | 97.12% | Complete
| Pagirinya 2 | 15474 | 20394 |  | 43.14% | 56.86% |  | 15140 | 97.84% | Complete | 20010 | 98.12% | Complete
Adjumani West | Agojo | 3050 | 4142 |  | 42.41% | 57.59% |  | 2962 | 97.11% | Complete | 4016 | 96.96% | Complete
| Mungula 1 | 5786 | 753 |  | 88.48% | 11.52% |  | 5749 | 99.36% | Complete | 735 | 97.61% | Complete
| Mirieyi | 5271 | 1940 |  | 73.1% | 26.9% |  | 5218 | 98.99% | Complete | 1911 | 98.51% | Complete
| Maaji 1 | 483 | 66 |  | 87.98% | 12.02% |  | 483 | 100% | Complete | 66 | 100% | Complete
| Maaji 2 | 12358 | 4376 |  | 73.85% | 26.15% |  | 12234 | 99% | Complete | 4238 | 96.85% | Complete
| Maaji 3 | 11589 | 3502 |  | 76.79% | 23.21% |  | 11344 | 97.89% | Complete | 3354 | 95.77% | Complete |  | 5734 | 49.48% | 1728 | 49.34%
TOTAL |  | 149853 | 61502 |  | 70.9% | 29.1% |  | 147845 | 98.66% | Complete | 60105 | 97.73% | Complete |  | 15306 | 10.21% | 4050 | 6.585%
Daily Distribution Summaries
| Distribution Date | 2021-01-04 |  |  |  | 2021-01-05 |  |  |  | 2021-01-06 |  |  |  | 2021-01-07 |  |  |  | 2021-01-08 |  |  |  | 2021-01-11
| Modality | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food
Settlement | FDP
Adjumani East | Ayilo 2 | 5660 | 53.87% | 2244 | 56.62% | 4432 | 42.9% | 1742 | 42.02% |  |  | 241 | 5.6%
| Ayilo 1 | [12 empty] | 8782 | 41.1% | 2625 | 46.95% | 8305 | 39.15% | 1988 | 34.57% | 3548 | 16.97% | 1377 | 22.56%
| Alere | [16 empty] | 4585 | 69.35% | 1178 | 73.35% | 1978 | 30.03% | 452 | 27.36%
| Baratuku | [12 empty] | 2816 | 44.25% | 561 | 34.72% | 3318 | 53.11% | 1151 | 65.77%
| Boroli | 4919 | 42.66% | 1126 | 38.52% | 6027 | 53.26% | 1919 | 59.89%
| Nyumanzi | [8 empty] | 9642 | 28.63% | 2651 | 38.65% | 13285 | 39.63% | 3041 | 43.3% | 6305 | 18.83% | 922 | 13.04% | 4046 | 12.1% | 493 | 6.85%
| Olua | [8 empty] | 5200 | 71.33% | 1711 | 85.68% | 1843 | 25.7% | 345 | 16.3%
| Pagirinya 2 | 4585 | 28.61% | 4336 | 21.8% | 5401 | 34.29% | 5203 | 26.08% | 4275 | 27.33% | 5366 | 26.62% | 915 | 5.9% | 4614 | 22.66% | 24 | 0.16% | 488 | 2.41%
Adjumani West | Agojo | 2246 | 72.71% | 1974 | 47.9% | 716 | 23.48% | 2042 | 49.3%
| Mungula 1 | 5003 | 85.36% | 625 | 94.13% | 746 | 12.89% | 110 | 14.61%
| Mirieyi | [8 empty] | 5142 | 96.67% | 1663 | 90.92% | 76 | 1.44% | 248 | 12.78%
| Maaji 1 | 483 | 100% | 66 | 100%
| Maaji 2 |  |  |  |  | 6338 | 50.67% | 1955 | 46.26% | 5697 | 45.9% | 2136 | 49.43% | 199 | 1.61% | 147 | 3.36%
| Maaji 3 | [16 empty] | 5610 | 47.17% | 1326 | 51.97% | 5734 | 49.48% | 1728 | 49.34%
TOTAL |  | 22896 | 15.28% | 10371 | 16.86% | 23660 | 15.79% | 12971 | 21.09% | 29956 | 19.99% | 13768 | 22.39% | 27916 | 18.63% | 11581 | 18.83% | 28147 | 18.78% | 7053 | 11.47% | 15306 | 10.21% | 4050 | 6.585%

## GFA Cycle 12 2020
Gulu GFA Cycle 12, 2020 Distribution Update
Date: | 2020-12-22
Data | Population
| Distribution Date | Total |  |  | Modality Ratio |  |  | Overall Status | [6 empty] | 2020-12-22
| Modality | Cash | Food |  | Cash | Food |  | Cash |  |  | Food |  |  |  | Cash | % Cash | Food | % Food
Settlement | FDP | [6 empty] | Population | % Cash | Status | Population | % Food | Status
Kiryandongo | Magamaga | 26010 | 6838 |  | 79.18% | 20.82% |  | 25993 | 99.93% | Complete | 6739 | 98.55% | Complete
| Youth Centre | 26578 | 10411 |  | 71.85% | 28.15% |  | 26483 | 99.64% | Complete | 10303 | 98.96% | Complete
Palabek | Zone 1 |  | 5215 |  | 0% | 100% |  |  |  |  | 5136 | 98.49% | Complete
| Zone 5 |  | 17454 |  | 0% | 100% |  |  |  |  | 17045 | 97.66% | Complete
| Zone 4 |  | 25566 |  | 0% | 100% |  |  |  |  | 24924 | 97.49% | Complete |  |  |  | 2871 | 11.23%
TOTAL |  | 52588 | 65484 |  | 44.54% | 55.46% |  | 52476 | 99.79% |  | 64147 | 97.96% |  |  | 0 | 0% | 2871 | 4.384%
Daily Distribution Summaries
| Distribution Date | 2020-12-02 |  | 2020-12-03 |  | 2020-12-04 |  | 2020-12-07 |  | 2020-12-08 |  |  |  | 2020-12-09 |  |  |  | 2020-12-10 |  |  |  | 2020-12-11 |  |  |  | 2020-12-14 |  |  |  | 2020-12-15 |  |  |  | 2020-12-16 |  |  |  | 2020-12-17 |  |  |  | 2020-12-18 |  |  |  | 2020-12-21 |  |  |  | 2020-12-22
| Modality | Food | % Food | Food | Food% | Food | % Food | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food
Settlement | FDP
Kiryandongo | Magamaga | [8 empty] | 6777 | 26.04% | 1868 | 27.44% | 7168 | 27.55% | 1912 | 28.05% | 8040 | 30.91% | 2158 | 31.56% | 4008 | 15.41% | 801 | 11.71%
| Youth Centre | [24 empty] | 7669 | 28.85% | 3083 | 29.73% | 8016 | 30.15% | 3417 | 32.95% | 7643 | 28.76% | 2709 | 26.02% | 3155 | 11.87% | 1094 | 10.51%
Palabek | Zone 1 | 2750 | 52.73% | 2386 | 45.75%
| Zone 5 |  |  |  |  | 3271 | 18.79% | 3085 | 17.72% |  |  | 2494 | 14.29% |  |  | 3843 | 22.02% |  |  | 3488 | 19.98% |  |  | 864 | 4.95%
| Zone 4 | [26 empty] | 3423 | 13.45% |  |  | 2750 | 10.78% |  |  | 3990 | 15.64% |  |  | 4389 | 17.2% |  |  | 3392 | 13.29% |  |  | 4117 | 16.1% |  |  | 2871 | 11.23%
TOTAL |  | 2750 | 4.199% | 2386 | 3.644% | 3271 | 4.995% | 3085 | 4.711% | 6777 | 12.89% | 4362 | 6.661% | 7168 | 13.7% | 5733 | 8.825% | 8040 | 15.29% | 5646 | 8.622% | 4008 | 7.622% | 1665 | 2.543% | 7669 | 14.58% | 6506 | 9.935% | 8016 | 15.24% | 6167 | 9.418% | 7643 | 14.53% | 6699 | 10.23% | 3155 | 5.999% | 5483 | 8.373% | 0 | 0% | 3392 | 5.18% | 0 | 0% | 4117 | 6.287% | 0 | 0% | 2871 | 4.384%

## GFA Cycle 11 2020
Gulu GFA Cycle 11, 2020 Distribution Update
Date: | 2020-11-30
Data | Population
| Distribution Date | Total |  |  | Modality Ratio |  |  | Overall Status | [6 empty] | 2020-11-30
| Modality | Cash | Food |  | Cash | Food |  | Cash |  |  | Food |  |  |  | Cash | % Cash | Food | % Food
Settlement | FDP | [6 empty] | Population | % Cash | Status | Population | % Food | Status
Adjumani East | Ayilo 2 | 10159 | 4320 |  | 70.16% | 29.84% |  | 10070 | 99.12% | Complete | 4250 | 98.38% | Complete
| Ayilo 1 | 20196 | 6295 |  | 76.24% | 23.76% |  | 20041 | 99.23% | Complete | 6174 | 98.08% | Complete
| Alere | 6677 | 1542 |  | 81.24% | 18.76% |  | 6641 | 99.46% | Complete | 1528 | 99.09% | Complete
| Baratuku | 6208 | 1795 |  | 77.57% | 22.43% |  | 6135 | 98.82% | Complete | 1751 | 97.55% | Complete
| Boroli | 11355 | 3221 |  | 77.9% | 22.1% |  | 11059 | 97.39% | Complete | 3155 | 97.95% | Complete
| Nyumanzi | 33206 | 7278 |  | 82.02% | 17.98% |  | 33084 | 99.63% | Complete | 7200 | 98.93% | Complete
| Olua | 7485 | 2217 |  | 77.15% | 22.85% |  | 6965 | 93.05% | Complete | 2149 | 96.93% | Complete
| Pagirinya 2 | 15279 | 20441 |  | 42.77% | 57.23% |  | 14929 | 97.71% | Complete | 19942 | 97.56% | Complete
Adjumani West | Agojo | 3033 | 4080 |  | 42.64% | 57.36% |  | 2968 | 97.86% | Complete | 4007 | 98.21% | Complete
| Mungula 1 | 5672 | 860 |  | 86.83% | 13.17% |  | 5594 | 98.62% | Complete | 843 | 98.02% | Complete
| Mirieyi | 5108 | 1966 |  | 72.21% | 27.79% |  | 4998 | 97.85% | Complete | 1941 | 98.73% | Complete
| Maaji 1 | 483 | 66 |  | 87.98% | 12.02% |  | 483 | 100% | Complete | 66 | 100% | Complete
| Maaji 2 | 12422 | 4412 |  | 73.79% | 26.21% |  | 12381 | 99.67% | Complete | 4308 | 97.64% | Complete |  | 645 | 5.19% | 1562 | 35.4%
| Maaji 3 | 11501 | 3554 |  | 76.39% | 23.61% |  | 11379 | 98.94% | Complete | 3442 | 96.85% | Complete |  | 6958 | 60.5% | 532 | 14.97%
Kiryandongo | Magamaga | 25742 | 6746 |  | 79.24% | 20.76% |  | 25545 | 99.23% | Complete | 6603 | 97.88% | Complete
| Youth Centre | 26306 | 10115 |  | 72.23% | 27.77% |  | 26150 | 99.41% | Complete | 9914 | 98.01% | Complete
Palabek | Zone 1 |  | 5190 |  | 0% | 100% |  |  |  |  | 5083 | 97.94% | Complete
| Zone 5 |  | 17592 |  | 0% | 100% |  |  |  |  | 17045 | 96.89% | Complete
| Zone 4 |  | 25386 |  | 0% | 100% |  |  |  |  | 24299 | 95.72% | Complete
TOTAL |  | 200832 | 127076 |  | 61.25% | 38.75% |  | 198422 | 98.8% |  | 123700 | 97.34% |  |  | 7603 | 3.786% | 2094 | 1.648%
Daily Distribution Summaries
| Distribution Date | 2020-11-05 |  | 2020-11-06 |  | 2020-11-09 |  | 2020-11-10 |  |  |  | 2020-11-11 |  |  |  | 2020-11-12 |  |  |  | 2020-11-13 |  |  |  | 2020-11-16 |  |  |  | 2020-11-17 |  |  |  | 2020-11-18 |  |  |  | 2020-11-20 |  |  |  | 2020-11-23 |  |  |  | 2020-11-24 |  |  |  | 2020-11-25 |  |  |  | 2020-11-26 |  |  |  | 2020-11-27 |  |  |  | 2020-11-30
| Modality | Food | % Food | Food | Food% | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food | Cash | % Cash | Food | % Food
Settlement | FDP
Adjumani East | Ayilo 2 | [22 empty] | 3236 | 30.78% | 1246 | 31.41% | 4655 | 44.98% | 1268 | 30.69% | 2191 | 21.57% | 1736 | 40.19%
| Ayilo 1 | [34 empty] | 2182 | 10.41% | 806 | 15.33% | 5388 | 25.88% | 1398 | 25.78% | 3441 | 16.63% | 1244 | 22.19% | 7004 | 34.03% | 1135 | 19.61% | 2026 | 10.03% | 1591 | 25.27%
| Alere | [40 empty] | 1326 | 87.76% |  |  |  |  | 4128 | 61.94% | 114 | 7.42% | 2513 | 37.64% | 88 | 5.71%
| Baratuku | [38 empty] | 4564 | 71.9% |  |  | 1571 | 25.31% | 1143 | 65.17% |  |  | 608 | 33.87%
| Boroli | [6 empty] | 3354 | 29.54% | 704 | 23.17% | 5567 | 49.03% | 1604 | 52.78% | 2138 | 18.83% | 614 | 20.2% |  |  | 233 | 7.23%
| Nyumanzi | [24 empty] | 2030 | 30.2% |  |  | 1852 | 27.45% | 4437 | 13.18% | 685 | 10.15% | 5578 | 16.64% | 1010 | 14.62% | 6207 | 18.57% | 959 | 13.6% | 13524 | 40.67% | 537 | 7.44% | 3338 | 10.05% | 127 | 1.74%
| Olua | [26 empty] | 6965 | 93.05% |  |  |  |  | 1869 | 93.22% |  |  | 280 | 12.63%
| Pagirinya 2 | [8 empty] | 2029 | 10.26% |  |  | 2901 | 14.67% | 4400 | 28.37% | 2502 | 12.65% | 2999 | 19.43% | 1998 | 10.05% | 4365 | 28.57% | 1964 | 9.69% | 3165 | 97.71% | 3158 | 15.59% |  |  | 1470 | 7.22% |  |  | 3920 | 19.18%
Adjumani West | Agojo | [6 empty] | 1880 | 61.98% | 1244 | 30.49% | 1088 | 35.87% | 2165 | 53.06% |  |  | 598 | 14.66%
| Mungula 1 | [6 empty] | 4496 | 79.27% | 531 | 61.74% | 1098 | 19.36% | 312 | 36.28%
| Mirieyi | [14 empty] | 3767 | 71.89% | 1528 | 83.32% | 1231 | 24.1% | 413 | 21.01%
| Maaji 1 | [18 empty] | 483 | 100% | 66 | 100%
| Maaji 2 | [50 empty] | 6506 | 51.83% | 1198 | 28.61% | 5230 | 42.01% | 1548 | 35.79% | 645 | 5.19% | 1562 | 35.4%
| Maaji 3 | [52 empty] | 1824 | 57% | 4421 | 38.12% | 1086 | 32.41% | 6958 | 60.5% | 532 | 14.97%
Kiryandongo | Magamaga | [22 empty] | 6870 | 26.69% | 2168 | 32.27% | 8386 | 32.58% | 1924 | 28.58% | 7289 | 28.32% | 2122 | 31.46% | 3000 | 11.65% | 389 | 5.77%
| Youth Centre | [6 empty] | 5121 | 19.46% | 2056 | 20.4% | 6802 | 25.85% | 2670 | 26.49% | 8066 | 30.65% | 3356 | 33.29% | 6161 | 23.42% | 1839 | 18.18%
Palabek | Zone 1 | 2695 | 51.93% | 2388 | 46.01%
| Zone 5 |  |  |  |  | 5256 | 30.04% |  |  | 3390 | 19.37% |  |  | 3248 | 18.56% |  |  | 2914 | 16.65% |  |  | 2232 | 12.69%
| Zone 4 | [24 empty] | 86 | 0.34 |  |  | 4460 | 17.84 |  |  | 4517 | 18.04 |  |  | 3459 | 13.69 |  |  | 3476 | 13.82 |  |  | 3063 | 12.09 |  |  | 3150 | 12.42 |  |  | 2010 | 7.92% |  |  | 2010 | 0.0792
TOTAL |  | 2695 |  | 2388 | [5 empty] | 9954 |  | 14555 |  | 12900 |  | 18371 |  | 11512 |  | 10874 |  | 6781 |  | 14471 |  | 7359 |  | 23171 | 11.5% | 12662 | 10.13% | 13917 | 6.897% | 12399 | 9.927% | 10760 | 5.312% | 9864 | 7.882% | 16159 | 7.976% | 7159 | 5.707% | 18536 | 9.169% | 5987 | 4.765% | 14470 | 7.164% | 5134 | 4.075% | 11045 | 5.483% | 6711 | 5.305% | 9651 | 4.803% | 4644 | 3.663% | 7603 | 3.786% | 2094 | 1.648%